## Tabelle1
Date of brainstorming | Software |  | Hardware |  | Management Update
| Abhilash | Sahana | Badhreesh | Xavier
2016-05-10 | DONE : - first step in dev. Board Intel Atom: - loaded OS Linux TOBEDONE: - In the process of loading first program (LED Blink) in order to master the Integrated Development Environment | DONE: - Working with Linux TO BE DONE: - Resaearch on voice recognition | DONE: - Looking up on LiFi technology TOBEDONE: - continue research on Lifi, find the right serial-LiFi module to be implemented - Document the research on LiFi | DONE: - Lookup for different hardware peripherals (power outputs) - Study of the datasheet of the Intel Atom & ARM uC TOBEDONE: - Start schematics of the wearable device | Work Organization: - Group work on Wednesday afternoons (mandatory + extendable) - Brainstorming every Tuesday at 4pm
5/12/2016 (triggerred due to scope change in the project) |  |  | Identify the following components: 1) Microphone 2) Speaker 3) Lifi Module 4) Touch pad The components shall have an interface comaptible with the processors interfaces. It should be low in power consumption and cost. The Lifi module should preferrably have a standard interface to a PC inorder to be integrated to the server. | Identify the following components: 1) Fingerprint sensor 2) Battery 3) Charging circuit The components shall have an interface comaptible with the processors interfaces. It should be low in power consumption and cost. | Project scope change: Meeting The server is decided to be retained as the existing implementatoion on the Mac. The wearable device shall only be developed under the scope of this project. The following decisions were taken regarding the features and plan for demo: The base plan: The wearable device shall be redesigned, reducing size and power consumption. The device shall be activiated on taping at a touch pad. When the device is activated, it shall be sending the voice signals to the server over Lifi. The device shall also receive voice reply from the server and play it in the speaker. Demo is planned with switching a light on and off over a voice command. The desirable plan: The werable device activation shall be done either using a finger print sensor or some voice based mechanism. The wearable device shall be based on Teensy hardware with the following components: 1) button switch 2) touch pad 3) microphone 4) speaker 5) battery 6) charging circuit 7) Lifi module The server part need to be interfaced with a Lifi module. The hardware and software required for this is also included in the scope of this project.